## RESUME
[8 empty] | Feature |  | Start | Yet | Remain
Main | Form | Core |  | Main | Form | Core |  | Main ► Form ► Core | System.Core | 2020-10-14 | 30 | 10
System | Form | Authentication | Login | System | Form | Authentication | Login | System ► Form ► Authentication ► Login | System.Authentication.Login | 2020-11-13 | 3 | 10
|  |  | Logout | System | Form | Authentication | Logout | System ► Form ► Authentication ► Logout | System.Authentication.Logout | 2020-11-13 | 1 | 10
Budgeting | Form | Budget | Submit | Budgeting | Form | Budget | Submit | Budgeting ► Form ► Budget ► Submit
|  |  | Revision | Budgeting | Form | Budget | Revision | Budgeting ► Form ► Budget ► Revision
|  | Budget Expense | Submit | Budgeting | Form | Budget Expense | Submit | Budgeting ► Form ► Budget Expense ► Submit
|  |  | Revision | Budgeting | Form | Budget Expense | Revision | Budgeting ► Form ► Budget Expense ► Revision
|  | Budget Expense Line | Submit | Budgeting | Form | Budget Expense Line | Submit | Budgeting ► Form ► Budget Expense Line ► Submit
|  |  | Revision | Budgeting | Form | Budget Expense Line | Revision | Budgeting ► Form ► Budget Expense Line ► Revision
|  | Budget Expense Line Ceiling | Submit | Budgeting | Form | Budget Expense Line Ceiling | Submit | Budgeting ► Form ► Budget Expense Line Ceiling ► Submit
|  |  | Revision | Budgeting | Form | Budget Expense Line Ceiling | Revision | Budgeting ► Form ► Budget Expense Line Ceiling ► Revision
|  | Budget Expense Line Ceiling Object | Submit | Budgeting | Form | Budget Expense Line Ceiling Object | Submit | Budgeting ► Form ► Budget Expense Line Ceiling Object ► Submit
|  |  | Revision | Budgeting | Form | Budget Expense Line Ceiling Object | Revision | Budgeting ► Form ► Budget Expense Line Ceiling Object ► Revision
|  | Budget Type | Submit | Budgeting | Form | Budget Type | Submit | Budgeting ► Form ► Budget Type ► Submit
|  |  | Revision | Budgeting | Form | Budget Type | Revision | Budgeting ► Form ► Budget Type ► Revision
| Report | Data List | Budget Expense | Budgeting | Report | Data List | Budget Expense | Budgeting ► Report ► Data List ► Budget Expense
|  |  | Budget Expense Line | Budgeting | Report | Data List | Budget Expense Line | Budgeting ► Report ► Data List ► Budget Expense Line
|  |  | Budget Expense Line Ceiling | Budgeting | Report | Data List | Budget Expense Line Ceiling | Budgeting ► Report ► Data List ► Budget Expense Line Ceiling
|  |  | Budget Expense Line Ceiling Object | Budgeting | Report | Data List | Budget Expense Line Ceiling Object | Budgeting ► Report ► Data List ► Budget Expense Line Ceiling Object
|  |  | BudgetType | Budgeting | Report | Data List | BudgetType | Budgeting ► Report ► Data List ► BudgetType
Customer Relation | Form | Sales Order | Submit | Customer Relation | Form | Sales Order | Submit | Customer Relation ► Form ► Sales Order ► Submit
|  |  | Revision | Customer Relation | Form | Sales Order | Revision | Customer Relation ► Form ► Sales Order ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Order | Cancelation | Customer Relation ► Form ► Sales Order ► Cancelation
|  |  | Settlement | Customer Relation | Form | Sales Order | Settlement | Customer Relation ► Form ► Sales Order ► Settlement
|  | Sales Invoice | Submit | Customer Relation | Form | Sales Invoice | Submit | Customer Relation ► Form ► Sales Invoice ► Submit
|  |  | Revision | Customer Relation | Form | Sales Invoice | Revision | Customer Relation ► Form ► Sales Invoice ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Invoice | Cancelation | Customer Relation ► Form ► Sales Invoice ► Cancelation
|  |  | Settlement | Customer Relation | Form | Sales Invoice | Settlement | Customer Relation ► Form ► Sales Invoice ► Settlement
|  | Data List | Sales Order | Customer Relation | Form | Data List | Sales Order | Customer Relation ► Form ► Data List ► Sales Order
|  |  | Sales Invoice | Customer Relation | Form | Data List | Sales Invoice | Customer Relation ► Form ► Data List ► Sales Invoice
Finance | Form | Advance | Submit | Finance | Form | Advance | Submit | Finance ► Form ► Advance ► Submit
|  |  | Revision | Finance | Form | Advance | Revision | Finance ► Form ► Advance ► Revision
|  |  | Cancelation | Finance | Form | Advance | Cancelation | Finance ► Form ► Advance ► Cancelation
|  |  | Settlement | Finance | Form | Advance | Settlement | Finance ► Form ► Advance ► Settlement
|  | Payment Instruction | Submit | Finance | Form | Payment Instruction | Submit | Finance ► Form ► Payment Instruction ► Submit
|  |  | Revision | Finance | Form | Payment Instruction | Revision | Finance ► Form ► Payment Instruction ► Revision
|  |  | Cancelation | Finance | Form | Payment Instruction | Cancelation | Finance ► Form ► Payment Instruction ► Cancelation
|  |  | Settlement | Finance | Form | Payment Instruction | Settlement | Finance ► Form ► Payment Instruction ► Settlement
| Report | Data List | Advance | Finance | Report | Data List | Advance | Finance ► Report ► Data List ► Advance
|  |  | Payment Instruction | Finance | Report | Data List | Payment Instruction | Finance ► Report ► Data List ► Payment Instruction
|  | Data Form | Advance | Finance | Report | Data Form | Advance | Finance ► Report ► Data Form ► Advance
|  |  | Payment Instruction | Finance | Report | Data Form | Payment Instruction | Finance ► Report ► Data Form ► Payment Instruction
|  | Resume | Advance Request | Finance | Report | Resume | Advance Request | Finance ► Report ► Resume ► Advance Request
|  |  | Advance Settlement | Finance | Report | Resume | Advance Settlement | Finance ► Report ► Resume ► Advance Settlement
|  |  | Advance Aging | Finance | Report | Resume | Advance Aging | Finance ► Report ► Resume ► Advance Aging
|  |  | Advance Request To Settlement | Finance | Report | Resume | Advance Request To Settlement | Finance ► Report ► Resume ► Advance Request To Settlement
Production | Form | Bill Of Material | Submit | Production | Form | Bill Of Material | Submit | Production ► Form ► Bill Of Material ► Submit
|  |  | Revision | Production | Form | Bill Of Material | Revision | Production ► Form ► Bill Of Material ► Revision
|  | Bill Of Material Detail | Submit | Production | Form | Bill Of Material Detail | Submit | Production ► Form ► Bill Of Material Detail ► Submit
|  |  | Revision | Production | Form | Bill Of Material Detail | Revision | Production ► Form ► Bill Of Material Detail ► Revision
|  | Material Product Assembly | Submit | Production | Form | Material Product Assembly | Submit | Production ► Form ► Material Product Assembly ► Submit
|  |  | Revision | Production | Form | Material Product Assembly | Revision | Production ► Form ► Material Product Assembly ► Revision
|  | Material Product Assembly Version | Submit | Production | Form | Material Product Assembly Version | Submit | Production ► Form ► Material Product Assembly Version ► Submit
|  |  | Revision | Production | Form | Material Product Assembly Version | Revision | Production ► Form ► Material Product Assembly Version ► Revision
|  | Material Product Component | Submit | Production | Form | Material Product Component | Submit | Production ► Form ► Material Product Component ► Submit
|  |  | Revision | Production | Form | Material Product Component | Revision | Production ► Form ► Material Product Component ► Revision
| Report | Data List | Bill Of Material | Production | Report | Data List | Bill Of Material | Production ► Report ► Data List ► Bill Of Material
|  |  | Bill Of Material Detail | Production | Report | Data List | Bill Of Material Detail | Production ► Report ► Data List ► Bill Of Material Detail
|  |  | Material Product Assembly | Production | Report | Data List | Material Product Assembly | Production ► Report ► Data List ► Material Product Assembly
|  |  | Material Product Assembly Version | Production | Report | Data List | Material Product Assembly Version | Production ► Report ► Data List ► Material Product Assembly Version
|  |  | Material Product Component | Production | Report | Data List | Material Product Component | Production ► Report ► Data List ► Material Product Component
Project | Form | Project | Submit | Project | Form | Project | Submit | Project ► Form ► Project ► Submit
|  |  | Revision | Project | Form | Project | Revision | Project ► Form ► Project ► Revision
|  | Project Section | Submit | Project | Form | Project Section | Submit | Project ► Form ► Project Section ► Submit
|  |  | Revision | Project | Form | Project Section | Revision | Project ► Form ► Project Section ► Revision
|  | Project Section Item | Submit | Project | Form | Project Section Item | Submit | Project ► Form ► Project Section Item ► Submit
|  |  | Revision | Project | Form | Project Section Item | Revision | Project ► Form ► Project Section Item ► Revision
|  | Project Section Item Work | Submit | Project | Form | Project Section Item Work | Submit | Project ► Form ► Project Section Item Work ► Submit
|  |  | Revision | Project | Form | Project Section Item Work | Revision | Project ► Form ► Project Section Item Work ► Revision
| Report | Data List | Project | Project | Report | Data List | Project | Project ► Report ► Data List ► Project
|  |  | Project Section | Project | Report | Data List | Project Section | Project ► Report ► Data List ► Project Section
|  |  | Project Section Item | Project | Report | Data List | Project Section Item | Project ► Report ► Data List ► Project Section Item
|  |  | Project Section Item Work | Project | Report | Data List | Project Section Item Work | Project ► Report ► Data List ► Project Section Item Work
Supply Chain | Form | Procurement Requisition | Submit | Supply Chain | Form | Procurement Requisition | Submit | Supply Chain ► Form ► Procurement Requisition ► Submit
|  |  | Revision | Supply Chain | Form | Procurement Requisition | Revision | Supply Chain ► Form ► Procurement Requisition ► Revision
|  |  | Cancelation | Supply Chain | Form | Procurement Requisition | Cancelation | Supply Chain ► Form ► Procurement Requisition ► Cancelation
|  |  | Settlement | Supply Chain | Form | Procurement Requisition | Settlement | Supply Chain ► Form ► Procurement Requisition ► Settlement
|  | Purchase Order | Submit | Supply Chain | Form | Purchase Order | Submit | Supply Chain ► Form ► Purchase Order ► Submit
|  |  | Revision | Supply Chain | Form | Purchase Order | Revision | Supply Chain ► Form ► Purchase Order ► Revision
|  |  | Cancelation | Supply Chain | Form | Purchase Order | Cancelation | Supply Chain ► Form ► Purchase Order ► Cancelation
|  |  | Settlement | Supply Chain | Form | Purchase Order | Settlement | Supply Chain ► Form ► Purchase Order ► Settlement
| Report | Data List | Procurement Requisition | Supply Chain | Report | Data List | Procurement Requisition | Supply Chain ► Report ► Data List ► Procurement Requisition
|  |  | Purchase Order | Supply Chain | Report | Data List | Purchase Order | Supply Chain ► Report ► Data List ► Purchase Order

## MAIN
ID | LEAD | [7 empty] | U/I FORM | [9 empty] | API | [11 empty] | DATABASE | [11 empty] | REDIS
| REFERENCE ID | LEAD DAYS | PERENCANAAN |  |  | REALISASI |  |  | KOMPONEN | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN |  |  | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN |  |  | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI
|  |  | DURASI | TANGGAL |  | DURASI | TANGGAL |  |  |  | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL | [5 empty] | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL | [5 empty] | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL |  |  |  | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL
|  |  |  | AWAL | AKHIR |  | AWAL | AKHIR |  |  |  | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR | [5 empty] | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR | [5 empty] | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR |  |  |  | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR
System.Core |  | 0 | 30 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13 | [26 empty] | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13 | [10 empty] | System.Core | 2020-11-13
|  | 0 | [28 empty] | ■ | Stored Procedure
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionBranch_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionBranch_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionBranch_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionCompany_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionCompany_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionCompany_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionRegional_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionRegional_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionRegional_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [28 empty] | ■ | Table
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionBranch | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionCompany | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionRegional | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_UserRole | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Parameter | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Partition_RemovableRecord_Key | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Partition_RemovableRecord_Parameter | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Schema | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Table | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_User | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_LDAPUserToPerson | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_UserToLDAPUser | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_UserToUserRole | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblLDAPObject_User | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblRotateLog_API | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblRotateLog_FailedUserLogin | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
System.Authentication.Login | System.Core | 0 | 5 | 2020-11-13 | 2020-11-18 | 3 | 2020-11-13 | 2020-11-16 | [14 empty] | 5 | 2020-11-13 | 2020-11-18 | 2020-11-13 | 2020-11-18 | 3 | 2020-11-13 | 2020-11-16 |  |  |  |  | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [10 empty] | System.Authentication.Login | 2020-11-16
|  | 0 | [7 empty] | Mulyadi | [9 empty] | - | authentication.general.setLogin | Teguh | 3 | 2020-11-13 | 2020-11-16 | 2020-11-13 | 2020-11-16 | 3 | 2020-11-13 | 2020-11-16 | ■ | Stored Procedure
|  | 0 | [17 empty] | - | authentication.general.setLoginBranchAndUserRole | Teguh | 4 | 2020-11-14 | 2020-11-18 | 2020-11-14 | 2020-11-18 | 2 | 2020-11-13 | 2020-11-15 |  | - | dbERPReborn.SchSysConfig.Func_TblLog_UserLoginSession_SET | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblLog_UserLoginSession_INSERT | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblLog_UserLoginSession_UPDATE | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [28 empty] | ■ | Table
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.TblLog_UserLoginSession | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
System.Authentication.Logout | System.Core | 0 | 1 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [14 empty] | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 |  |  |  |  | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [10 empty] | System.Authentication.Logout | 2020-11-14
|  | 0 | [7 empty] | Mulyadi | [9 empty] | - | authentication.general.setLogout | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | ■ | Stored Procedure
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.FuncSys_General_SetUserSessionLogout | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | #REF! | [28 empty] | ■ | Table
Formulas:
TANGGAL = IF(COUNTA([TANGGAL], [TANGGAL], [TANGGAL], [TANGGAL])=0, "", MIN([TANGGAL], [TANGGAL], [TANGGAL], [TANGGAL]))
TANGGAL = IF(COUNTA([TANGGAL, row below]:AQ34)=0, "", MIN([TANGGAL, row below]:AQ34))
AKHIR = IF(COUNTA([AKHIR], [AKHIR], [AKHIR], [AKHIR])=0, "", MAX([AKHIR], [AKHIR], [AKHIR], [AKHIR]))
AKHIR = IF(COUNTA([AKHIR, row below]:AR34)=0, "", MAX([AKHIR, row below]:AR34))
PERENCANAAN + LEAD TIME = IF(COUNT([PERENCANAAN + LEAD TIME, row below]:AS34)=0, "", MIN([PERENCANAAN + LEAD TIME, row below]:AS34))
PERENCANAAN + LEAD TIME = IF(OR(EXACT([PERENCANAAN],""), EXACT([TANGGAL],"")), "", [TANGGAL]+[LEAD DAYS])

## PARAMETER
VLOOKUP HEIGHT | 1000
Current Date Time | 2021-11-08 18:16