## PARAMETER
2025-02-19

## TIME SCHEDULE
TASK DESCRIPTION |  |  |  |  | TASK STATUS | FEBRUARI 2025 | [9 empty] | MARET 2025 | [30 empty] | APRIL 2025
[6 empty] | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1. | Rekomposisi & Optimize Existing Backend Object
|  |  | a. | SQL Object | bar: FEBRUARI 2025 19 to FEBRUARI 2025 21
|  |  | b. | API | bar: FEBRUARI 2025 19 to FEBRUARI 2025 21
2. | Create New BackEnd Object
| A. | Form |  |  | 0%
|  | b.1. | Chart Of Account Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | b.2. | Journal Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.1. | Budget Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.2. | Budget Expense Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.3. | Budget Expense Line Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.4. | Budget Expense Line Ceiling Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.5. | Budget Expense Line Ceiling Objects Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.6. | Combined Budget Section Detail Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.1. | Customer Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.2. | Prospective Customer Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.3. | Sales Contract Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.4. | Sales Order Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.5. | Sales Contract Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | d.6. | Sales Quotation Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.1. | Advance Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.2. | Advance Payment Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.3. | Advance Settlement Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.4. | Credit Note Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.5. | Debit Note Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.6. | Payment Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.7. | Payment Funding Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.8. | Payment Instruction Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.9. | Purchase Invoice Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.10. | Purchase Proforma Invoice Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.11. | Sales Invoice Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.12. | Sales Invoice Requisition Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | f.1. | Goods Identity Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | g.1. | Worker Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | g.2. | Worker Career Internal Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | h.1. | Bill Of Material Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | h.2. | Material Product Assembly Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | h.3. | Material Product Component Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | i.1. | Project Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | i.2. | Project Section Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | i.3. | Project Section Item Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | i.4. | Project Section Item Work Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.1. | Delivery Order Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.2. | Material Service Requisition Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.3. | Order Picking Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.4. | Order Picking Requisition Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.5. | Purchase Order Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.6. | Purchase Requisition Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.7. | Supplier Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.8. | Warehouse Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.9. | Warehouse Inbound Order Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.10. | Warehouse Outound Order Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | j.11. | Warehouse Type Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | k.1. | Tax Tarif Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | k.2. | Tax Type Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | k.3. | Transaction Tax Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
| B. | Data List |  |  | 51.28%
|  | b.1. | Chart Of Account List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | c.1. | Budget List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.2. | Budget Expense List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.3. | Budget Expense Line List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.4. | Budget Expense Line Ceiling List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.5. | Budget Expense Line Ceiling Objects List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | c.6. | Combined Budget Section Detail List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.1. | Advance List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.2. | Advance Payment List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.3. | Advance Settlement List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.4. | Credit Note List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.5. | Debit Note List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.6. | Payment List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.7. | Payment Funding List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.8. | Payment Instruction List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.9. | Purchase Invoice List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.10. | Purchase Proforma Invoice List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.11. | Sales Invoice List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | e.12. | Sales Invoice Requisition List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
| C. | Data Report
|  | e.1. | Advance To Advance Payment |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.2. | Advance To Advance Settlement |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.3. | Advance Payment To Payment |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.4. | Payment Instruction To Payment |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.5. | Purchase Order To Payment Instruction |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.6. | Sales Invoice To Sales Invoice Requisition |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm