## TIME SCHEDULE
Legenda PIC TP : Teguh Pratama, IM : Icha Mailinda, WS : Wisnu, MR : M. Rizal, SY : Suyanto
TASK DESCRIPTION |  |  |  |  | TASK STATUS | FEBRUARI 2025 | [9 empty] | MARET 2025 | [30 empty] | APRIL 2025 | [30 empty] | MEI 2025
[6 empty] | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1. | Rekomposisi & Optimize Existing Backend Object |  |  |  | 100%
|  |  | a. | SQL Object | 100% | bar: FEBRUARI 2025 19 to FEBRUARI 2025 21
|  |  | b. | API | 100% | bar: FEBRUARI 2025 19 to FEBRUARI 2025 21
2. | Create New BackEnd Object |  |  |  | 37.04%
| A. | Form |  |  | 50.48%
|  | c.1. | Chart Of Account Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | c.2. | Journal Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.1. | Budget Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.2. | Budget Expense Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.3. | Budget Expense Line Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.4. | Budget Expense Line Ceiling Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.5. | Budget Expense Line Ceiling Objects Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | d.6. | Combined Budget Section Detail Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | e.1. | Customer Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | e.2. | Prospective Customer Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | e.3. | Sales Contract Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | e.4. | Sales Addendum Form |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | e.5. | Sales Order Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | e.6. | Sales Quotation Form |  | 44.44%
|  |  | a. | SQL Object | 66.66%
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | f.1. | Advance Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: FEBRUARI 2025 24
|  |  | b. | API | 66.66% | bar: FEBRUARI 2025 25
|  |  | c. | WebForm
|  | f.2. | Advance Payment Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: FEBRUARI 2025 25
|  |  | b. | API | 66.66% | bar: FEBRUARI 2025 26
|  |  | c. | WebForm
|  | f.3. | Advance Settlement Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: FEBRUARI 2025 26
|  |  | b. | API | 66.66% | bar: FEBRUARI 2025 27
|  |  | c. | WebForm
|  | f.4. | Credit Note Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: FEBRUARI 2025 27
|  |  | b. | API | 66.66% | bar: FEBRUARI 2025 28
|  |  | c. | WebForm
|  | f.5. | Debit Note Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: FEBRUARI 2025 28
|  |  | b. | API | 66.66% | bar: MARET 2025 3
|  |  | c. | WebForm
|  | f.6. | Payment Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 3
|  |  | b. | API | 66.66% | bar: MARET 2025 4
|  |  | c. | WebForm
|  | f.7. | Payment Funding Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 4
|  |  | b. | API | 66.66% | bar: MARET 2025 5
|  |  | c. | WebForm
|  | f.8. | Payment Instruction Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 5
|  |  | b. | API | 66.66% | bar: MARET 2025 6
|  |  | c. | WebForm
|  | f.9. | Purchase Invoice Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 6
|  |  | b. | API | 66.66% | bar: MARET 2025 7
|  |  | c. | WebForm
|  | f.10. | Purchase Proforma Invoice Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 7
|  |  | b. | API | 66.66% | bar: MARET 2025 10
|  |  | c. | WebForm
|  | f.11. | Sales Invoice Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 10
|  |  | b. | API | 66.66% | bar: MARET 2025 11
|  |  | c. | WebForm
|  | f.12. | Sales Invoice Requisition Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 11
|  |  | b. | API | 66.66% | bar: MARET 2025 12
|  |  | c. | WebForm
|  | g.1. | Goods Identity Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 12
|  |  | b. | API | 66.66% | bar: MARET 2025 13
|  |  | c. | WebForm
|  | h.1. | Business Trip Form |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | h.2. | Timesheet Form |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | h.3. | Worker Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 13
|  |  | b. | API | 66.66% | bar: MARET 2025 14
|  |  | c. | WebForm
|  | h.4. | Worker Career Internal Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 14
|  |  | b. | API | 66.66% | bar: MARET 2025 17
|  |  | c. | WebForm
|  | i.1. | Bill Of Material Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 17
|  |  | b. | API | 66.66% | bar: MARET 2025 18
|  |  | c. | WebForm
|  | i.2. | Material Product Assembly Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 18
|  |  | b. | API | 66.66% | bar: MARET 2025 19
|  |  | c. | WebForm
|  | i.3. | Material Product Component Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 19
|  |  | b. | API | 66.66% | bar: MARET 2025 20
|  |  | c. | WebForm
|  | j.1. | Project Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 20
|  |  | b. | API | 66.66% | bar: MARET 2025 21
|  |  | c. | WebForm
|  | j.2. | Project Section Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 21
|  |  | b. | API | 66.66% | bar: MARET 2025 24
|  |  | c. | WebForm
|  | j.3. | Project Section Item Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 24
|  |  | b. | API | 66.66% | bar: MARET 2025 25
|  |  | c. | WebForm
|  | j.4. | Project Section Item Work Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 25
|  |  | b. | API | 66.66% | bar: MARET 2025 26
|  |  | c. | WebForm
|  | j.5. | Bill Of Quantity Form |  | 33.33%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 26
|  |  | b. | API | 33.33% | bar: MARET 2025 27
|  |  | c. | WebForm
|  | k.1. | Delivery Order Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 27
|  |  | b. | API | 66.66% | bar: MARET 2025 28
|  |  | c. | WebForm
|  | k.2. | Material Service Requisition Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 28
|  |  | b. | API | 66.66% | bar: APRIL 2025 2
|  |  | c. | WebForm
|  | k.3. | Order Picking Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 2
|  |  | b. | API | 66.66% | bar: APRIL 2025 3
|  |  | c. | WebForm
|  | k.4. | Order Picking Requisition Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 3
|  |  | b. | API | 66.66% | bar: APRIL 2025 4
|  |  | c. | WebForm
|  | k.5. | Purchase Order Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 4
|  |  | b. | API | 66.66% | bar: APRIL 2025 7
|  |  | c. | WebForm
|  | k.6. | Purchase Requisition Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 7
|  |  | b. | API | 66.66% | bar: APRIL 2025 8
|  |  | c. | WebForm
|  | k.7. | Supplier Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 8
|  |  | b. | API | 66.66% | bar: APRIL 2025 9
|  |  | c. | WebForm
|  | k.8. | Warehouse Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 9
|  |  | b. | API | 66.66% | bar: APRIL 2025 10
|  |  | c. | WebForm
|  | k.9. | Warehouse Inbound Order Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 10
|  |  | b. | API | 66.66% | bar: APRIL 2025 11
|  |  | c. | WebForm
|  | k.10. | Warehouse Outound Order Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 11
|  |  | b. | API | 66.66% | bar: APRIL 2025 14
|  |  | c. | WebForm
|  | k.11. | Warehouse Type Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 14
|  |  | b. | API | 66.66% | bar: APRIL 2025 15
|  |  | c. | WebForm
|  | l.1. | Tax Tarif Form |  | 44.44% | bar: APRIL 2025 15
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 16
|  |  | b. | API | 66.66%
|  |  | c. | WebForm
|  | l.2. | Tax Type Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 16
|  |  | b. | API | 66.66% | bar: APRIL 2025 17
|  |  | c. | WebForm
|  | l.3. | Transaction Tax Form |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: APRIL 2025 17
|  |  | b. | API | 66.66% | bar: APRIL 2025 21
|  |  | c. | WebForm
|  | z.1. | Main Form |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | z.2. | User Login |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | z.3. | User Logout |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | z.4. | Check Document |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
|  | z.5. | Check My Document |  | 100%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm | 100%
| B. | Data List |  |  | 60.63%
|  | a.1. | Menu List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.2. | Menu Action List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.3. | Menu Group List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.4. | Menu Group Member List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.5. | User List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.6. | User Role List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.7. | User Role Group List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.8. | User Role Group Member List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.9. | User Role Privileges List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.10. | Workflow List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.11. | Workflow Path List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.12. | Workflow Path Action List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.13. | Workflow Path Sequence List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | a.14. | Workflow Version List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | b.1. | Bank List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | b.2. | Bank Account List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | b.3. | Bank Branch List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | c.1. | Chart Of Account List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.1. | Budget List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.2. | Budget Expense List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.3. | Budget Expense Line List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.4. | Budget Expense Line Ceiling List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.5. | Budget Expense Line Ceiling Objects List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.6. | Combined Budget List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | d.7. | Combined Budget Section Detail List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.1. | Advance List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.2. | Advance Payment List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.3. | Advance Settlement List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.4. | Credit Note List (Sales Return) |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.5. | Debit Note List (Purchase Return) |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.6. | Payment List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.7. | Payment Funding List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | f.8. | Payment Instruction List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.9. | Purchase Invoice List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.10. | Purchase Proforma Invoice List |  | 0%
|  |  | a. | SQL Object
|  |  | b. | API
|  |  | c. | WebForm
|  | f.11. | Sales Invoice List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | f.12. | Sales Invoice Requisition List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | h.1. | Business Trip List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | h.2. | Timesheet List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | h.3. | Worker List |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 13
|  |  | b. | API | 66.66% | bar: MARET 2025 14
|  |  | c. | WebForm
|  | h.4. | Worker Career Internal List |  | 44.44%
|  |  | a. | SQL Object | 66.66% | bar: MARET 2025 14
|  |  | b. | API | 66.66% | bar: MARET 2025 17
|  |  | c. | WebForm
|  | j.1. | Project List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.2. | Project Section List |  | 22%
|  |  | a. | SQL Object | 33%
|  |  | b. | API | 33%
|  |  | c. | WebForm
|  | j.3. | Project Section Item List |  | 22%
|  |  | a. | SQL Object | 33%
|  |  | b. | API | 33%
|  |  | c. | WebForm
|  | j.4. | Project Section Item Work List |  | 22%
|  |  | a. | SQL Object | 33%
|  |  | b. | API | 33%
|  |  | c. | WebForm
|  | j.5. | Bill Of Quantity List |  | 22%
|  |  | a. | SQL Object | 33%
|  |  | b. | API | 33%
|  |  | c. | WebForm
|  | j.1. | Delivery Order List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.2. | Material Service Requisition List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.3. | Order Picking List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.4. | Order Picking Requisition List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.5. | Purchase Order List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.6. | Purchase Requisition List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.7. | Supplier List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.8. | Warehouse List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.9. | Warehouse Inbound Order List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.10. | Warehouse Outbound Order List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | j.11. | Warehouse Type List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | l.1. | Tax Tariff List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
|  | l.2. | Tax Type List |  | 66.67%
|  |  | a. | SQL Object | 100%
|  |  | b. | API | 100%
|  |  | c. | WebForm
| C. | Data Report |  |  | 0%
|  | c.1. | Balance Sheet |  | 0%
|  |  | a. | SQL Object | bar: APRIL 2025 21 to APRIL 2025 23
|  |  | b. | API | bar: APRIL 2025 22 to APRIL 2025 24
|  |  | c. | WebForm
|  | c.2. | General Ledger |  | 0%
|  |  | a. | SQL Object | bar: APRIL 2025 24 to APRIL 2025 25; APRIL 2025 28
|  |  | b. | API | bar: APRIL 2025 25; APRIL 2025 28 to APRIL 2025 29
|  |  | c. | WebForm
|  | c.3. | Profit Loss Report |  | 0%
|  |  | a. | SQL Object | bar: APRIL 2025 29 to APRIL 2025 31
|  |  | b. | API | bar: APRIL 2025 30 to APRIL 2025 31; MEI 2025 2
|  |  | c. | WebForm
|  | c.4. | Trial Balance Report |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 2; MEI 2025 5 to MEI 2025 6
|  |  | b. | API | bar: MEI 2025 5 to MEI 2025 7
|  |  | c. | WebForm
|  | e.1. | Sales Contract To Sales Invoice |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 7
|  |  | b. | API | bar: MEI 2025 8
|  |  | c. | WebForm
|  | f.1. | Advance Aging |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 8 to MEI 2025 9
|  |  | b. | API | bar: MEI 2025 9; MEI 2025 13
|  |  | c. | WebForm
|  | f.2. | Advance To Advance Payment |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 13
|  |  | b. | API | bar: MEI 2025 14
|  |  | c. | WebForm
|  | f.3. | Advance To Advance Settlement |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 14
|  |  | b. | API | bar: MEI 2025 15
|  |  | c. | WebForm
|  | f.4. | Advance Payment To Payment |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 15
|  |  | b. | API | bar: MEI 2025 16
|  |  | c. | WebForm
|  | f.5. | Payment Instruction To Payment |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 16
|  |  | b. | API | bar: MEI 2025 19
|  |  | c. | WebForm
|  | f.6. | Purchase Order To Payment Instruction |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 19
|  |  | b. | API | bar: MEI 2025 20
|  |  | c. | WebForm
|  | f.7. | Sales Invoice Requisition To Sales Invoice |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 20
|  |  | b. | API | bar: MEI 2025 21
|  |  | c. | WebForm
|  | f.8. | Account Payable (AP) Aging Report |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 21
|  |  | b. | API | bar: MEI 2025 22
|  |  | c. | WebForm
|  | f.9. | Account Receivable (AR) Aging Report |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 22
|  |  | b. | API | bar: MEI 2025 23
|  |  | c. | WebForm
|  | j.1. | Project Budget Report |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 23
|  |  | b. | API | bar: MEI 2025 26
|  |  | c. | WebForm
|  | j.2. | Project Spend Budget Report |  | 0%
|  |  | a. | SQL Object | bar: MEI 2025 26
|  |  | b. | API | bar: MEI 2025 27
|  |  | c. | WebForm