## RESUME
[8 empty] | Feature |  | Start | Yet | Remain | date
Main | Form | Core |  | Main | Form | Core |  | Main ► Form ► Core | System.Core | 2020-10-14 | 30 | 10
System | Form | Authentication | Login | System | Form | Authentication | Login | System ► Form ► Authentication ► Login | System.Authentication.Login | 2020-11-13 | 3 | 10
|  |  | Logout | System | Form | Authentication | Logout | System ► Form ► Authentication ► Logout | System.Authentication.Logout | 2020-11-13 | 1 | 10
Data Master | Form | Master | Submit | Data Master | Form | Master | Submit | Data Master ► Form ► Master ► Submit | Master | 2020-11-13 | 263 | #N/A
|  |  | Revision | Data Master | Form | Master | Revision | Data Master ► Form ► Master ► Revision | Master | 2020-11-13 | 263 | #N/A
|  |  | Delete | Data Master | Form | Master | Delete | Data Master ► Form ► Master ► Delete | Master | 2020-11-13 | 263 | #N/A
Accounting | Form | Journal | Submit | Accounting | Form | Journal | Submit | Accounting ► Form ► Journal ► Submit
|  |  | Revision | Accounting | Form | Journal | Revision | Accounting ► Form ► Journal ► Revision
|  |  | Posting | Accounting | Form | Journal | Posting | Accounting ► Form ► Journal ► Posting
| Report | Resume | General Ledger | Accounting | Report | Resume | General Ledger | Accounting ► Report ► Resume ► General Ledger
|  |  | Journal | Accounting | Report | Resume | Journal | Accounting ► Report ► Resume ► Journal
|  |  | Profit & Loss | Accounting | Report | Resume | Profit & Loss | Accounting ► Report ► Resume ► Profit & Loss
|  |  | Trial Balance | Accounting | Report | Resume | Trial Balance | Accounting ► Report ► Resume ► Trial Balance
Budgeting | Form | Budget | Submit | Budgeting | Form | Budget | Submit | Budgeting ► Form ► Budget ► Submit | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  |  | Revision | Budgeting | Form | Budget | Revision | Budgeting ► Form ► Budget ► Revision | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  | Budget Expense | Submit | Budgeting | Form | Budget Expense | Submit | Budgeting ► Form ► Budget Expense ► Submit | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  |  | Revision | Budgeting | Form | Budget Expense | Revision | Budgeting ► Form ► Budget Expense ► Revision | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  | Budget Expense Line | Submit | Budgeting | Form | Budget Expense Line | Submit | Budgeting ► Form ► Budget Expense Line ► Submit | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  |  | Revision | Budgeting | Form | Budget Expense Line | Revision | Budgeting ► Form ► Budget Expense Line ► Revision | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  | Budget Expense Line Ceiling | Submit | Budgeting | Form | Budget Expense Line Ceiling | Submit | Budgeting ► Form ► Budget Expense Line Ceiling ► Submit | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  |  | Revision | Budgeting | Form | Budget Expense Line Ceiling | Revision | Budgeting ► Form ► Budget Expense Line Ceiling ► Revision | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  | Budget Expense Line Ceiling Object | Submit | Budgeting | Form | Budget Expense Line Ceiling Object | Submit | Budgeting ► Form ► Budget Expense Line Ceiling Object ► Submit | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  |  | Revision | Budgeting | Form | Budget Expense Line Ceiling Object | Revision | Budgeting ► Form ► Budget Expense Line Ceiling Object ► Revision | Budgeting.Form.Budget | 2021-02-16 | 95 | #N/A
|  | Budget Type | Submit | Budgeting | Form | Budget Type | Submit | Budgeting ► Form ► Budget Type ► Submit
|  |  | Revision | Budgeting | Form | Budget Type | Revision | Budgeting ► Form ► Budget Type ► Revision
| Report | Data List | Budget Expense | Budgeting | Report | Data List | Budget Expense | Budgeting ► Report ► Data List ► Budget Expense
|  |  | Budget Expense Line | Budgeting | Report | Data List | Budget Expense Line | Budgeting ► Report ► Data List ► Budget Expense Line
|  |  | Budget Expense Line Ceiling | Budgeting | Report | Data List | Budget Expense Line Ceiling | Budgeting ► Report ► Data List ► Budget Expense Line Ceiling
|  |  | Budget Expense Line Ceiling Object | Budgeting | Report | Data List | Budget Expense Line Ceiling Object | Budgeting ► Report ► Data List ► Budget Expense Line Ceiling Object
|  |  | BudgetType | Budgeting | Report | Data List | BudgetType | Budgeting ► Report ► Data List ► BudgetType
Customer Relation | Form | Customer | Submit | Customer Relation | Form | Customer | Submit | Customer Relation ► Form ► Customer ► Submit
|  |  | Revision | Customer Relation | Form | Customer | Revision | Customer Relation ► Form ► Customer ► Revision
|  | Prospective Customer | Submit | Customer Relation | Form | Prospective Customer | Submit | Customer Relation ► Form ► Prospective Customer ► Submit
|  |  | Revision | Customer Relation | Form | Prospective Customer | Revision | Customer Relation ► Form ► Prospective Customer ► Revision
|  | Sales Contract | Submit | Customer Relation | Form | Sales Contract | Submit | Customer Relation ► Form ► Sales Contract ► Submit
|  |  | Revision | Customer Relation | Form | Sales Contract | Revision | Customer Relation ► Form ► Sales Contract ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Contract | Cancelation | Customer Relation ► Form ► Sales Contract ► Cancelation
|  | Sales Contract Addendum | Submit | Customer Relation | Form | Sales Contract Addendum | Submit | Customer Relation ► Form ► Sales Contract Addendum ► Submit
|  |  | Revision | Customer Relation | Form | Sales Contract Addendum | Revision | Customer Relation ► Form ► Sales Contract Addendum ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Contract Addendum | Cancelation | Customer Relation ► Form ► Sales Contract Addendum ► Cancelation
|  | Sales Invoice | Submit | Customer Relation | Form | Sales Invoice | Submit | Customer Relation ► Form ► Sales Invoice ► Submit
|  |  | Revision | Customer Relation | Form | Sales Invoice | Revision | Customer Relation ► Form ► Sales Invoice ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Invoice | Cancelation | Customer Relation ► Form ► Sales Invoice ► Cancelation
|  | Sales Order | Submit | Customer Relation | Form | Sales Order | Submit | Customer Relation ► Form ► Sales Order ► Submit
|  |  | Revision | Customer Relation | Form | Sales Order | Revision | Customer Relation ► Form ► Sales Order ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Order | Cancelation | Customer Relation ► Form ► Sales Order ► Cancelation
|  | Sales Quotation | Submit | Customer Relation | Form | Sales Quotation | Submit | Customer Relation ► Form ► Sales Quotation ► Submit
|  |  | Revision | Customer Relation | Form | Sales Quotation | Revision | Customer Relation ► Form ► Sales Quotation ► Revision
|  |  | Cancelation | Customer Relation | Form | Sales Quotation | Cancelation | Customer Relation ► Form ► Sales Quotation ► Cancelation
|  | Data List | Customer | Customer Relation | Form | Data List | Customer | Customer Relation ► Form ► Data List ► Customer
|  |  | Prospective Customer | Customer Relation | Form | Data List | Prospective Customer | Customer Relation ► Form ► Data List ► Prospective Customer
|  |  | Sales Contract | Customer Relation | Form | Data List | Sales Contract | Customer Relation ► Form ► Data List ► Sales Contract
|  |  | Sales Contract Addendum | Customer Relation | Form | Data List | Sales Contract Addendum | Customer Relation ► Form ► Data List ► Sales Contract Addendum
|  |  | Sales Invoice | Customer Relation | Form | Data List | Sales Invoice | Customer Relation ► Form ► Data List ► Sales Invoice
|  |  | Sales Order | Customer Relation | Form | Data List | Sales Order | Customer Relation ► Form ► Data List ► Sales Order
|  |  | Sales Quotation | Customer Relation | Form | Data List | Sales Quotation | Customer Relation ► Form ► Data List ► Sales Quotation
Finance | Form | Advance | Submit | Finance | Form | Advance | Submit | Finance ► Form ► Advance ► Submit
|  |  | Revision | Finance | Form | Advance | Revision | Finance ► Form ► Advance ► Revision
|  |  | Cancelation | Finance | Form | Advance | Cancelation | Finance ► Form ► Advance ► Cancelation
|  |  | Settlement | Finance | Form | Advance | Settlement | Finance ► Form ► Advance ► Settlement
|  | Bank Receive Money | Submit | Finance | Form | Bank Receive Money | Submit | Finance ► Form ► Bank Receive Money ► Submit
|  |  | Revision | Finance | Form | Bank Receive Money | Revision | Finance ► Form ► Bank Receive Money ► Revision
|  |  | Cancelation | Finance | Form | Bank Receive Money | Cancelation | Finance ► Form ► Bank Receive Money ► Cancelation
|  | Bank Spend Money | Submit | Finance | Form | Bank Spend Money | Submit | Finance ► Form ► Bank Spend Money ► Submit
|  |  | Revision | Finance | Form | Bank Spend Money | Revision | Finance ► Form ► Bank Spend Money ► Revision
|  |  | Cancelation | Finance | Form | Bank Spend Money | Cancelation | Finance ► Form ► Bank Spend Money ► Cancelation
|  | Debit Note | Submit | Finance | Form | Debit Note | Submit | Finance ► Form ► Debit Note ► Submit
|  |  | Revision | Finance | Form | Debit Note | Revision | Finance ► Form ► Debit Note ► Revision
|  |  | Cancelation | Finance | Form | Debit Note | Cancelation | Finance ► Form ► Debit Note ► Cancelation
|  | Payment Instruction | Submit | Finance | Form | Payment Instruction | Submit | Finance ► Form ► Payment Instruction ► Submit
|  |  | Revision | Finance | Form | Payment Instruction | Revision | Finance ► Form ► Payment Instruction ► Revision
|  |  | Cancelation | Finance | Form | Payment Instruction | Cancelation | Finance ► Form ► Payment Instruction ► Cancelation
|  |  | Settlement | Finance | Form | Payment Instruction | Settlement | Finance ► Form ► Payment Instruction ► Settlement
|  | Payment Voucher | Submit | Finance | Form | Payment Voucher | Submit | Finance ► Form ► Payment Voucher ► Submit
|  |  | Revision | Finance | Form | Payment Voucher | Revision | Finance ► Form ► Payment Voucher ► Revision
|  | Reimbursement | Submit | Finance | Form | Reimbursement | Submit | Finance ► Form ► Reimbursement ► Submit
|  |  | Revision | Finance | Form | Reimbursement | Revision | Finance ► Form ► Reimbursement ► Revision
| Report | Data Form | Advance | Finance | Report | Data Form | Advance | Finance ► Report ► Data Form ► Advance
|  |  | Payment Instruction | Finance | Report | Data Form | Payment Instruction | Finance ► Report ► Data Form ► Payment Instruction
|  | Data List | Advance | Finance | Report | Data List | Advance | Finance ► Report ► Data List ► Advance
|  |  | Bank Receive Money | Finance | Report | Data List | Bank Receive Money | Finance ► Report ► Data List ► Bank Receive Money
|  |  | Bank Spend Money | Finance | Report | Data List | Bank Spend Money | Finance ► Report ► Data List ► Bank Spend Money
|  |  | Debit Note | Finance | Report | Data List | Debit Note | Finance ► Report ► Data List ► Debit Note
|  |  | Payment Voucher | Finance | Report | Data List | Payment Voucher | Finance ► Report ► Data List ► Payment Voucher
|  |  | Payment Instruction | Finance | Report | Data List | Payment Instruction | Finance ► Report ► Data List ► Payment Instruction
|  |  | Reimbursement | Finance | Report | Data List | Reimbursement | Finance ► Report ► Data List ► Reimbursement
|  | Resume | Advance Request | Finance | Report | Resume | Advance Request | Finance ► Report ► Resume ► Advance Request
|  |  | Advance Settlement | Finance | Report | Resume | Advance Settlement | Finance ► Report ► Resume ► Advance Settlement
|  |  | Advance Aging | Finance | Report | Resume | Advance Aging | Finance ► Report ► Resume ► Advance Aging
|  |  | Advance Request To Settlement | Finance | Report | Resume | Advance Request To Settlement | Finance ► Report ► Resume ► Advance Request To Settlement
Human Resource | Form | Business Trip | Submit | Human Resource | Form | Business Trip | Submit | Human Resource ► Form ► Business Trip ► Submit
|  |  | Revision | Human Resource | Form | Business Trip | Revision | Human Resource ► Form ► Business Trip ► Revision
|  |  | Cancelation | Human Resource | Form | Business Trip | Cancelation | Human Resource ► Form ► Business Trip ► Cancelation
|  |  | Settlement | Human Resource | Form | Business Trip | Settlement | Human Resource ► Form ► Business Trip ► Settlement
|  | Piecemeal | Submit | Human Resource | Form | Piecemeal | Submit | Human Resource ► Form ► Piecemeal ► Submit
|  |  | Revision | Human Resource | Form | Piecemeal | Revision | Human Resource ► Form ► Piecemeal ► Revision
|  |  | Cancelation | Human Resource | Form | Piecemeal | Cancelation | Human Resource ► Form ► Piecemeal ► Cancelation
|  | Timesheet | Submit | Human Resource | Form | Timesheet | Submit | Human Resource ► Form ► Timesheet ► Submit
|  |  | Revision | Human Resource | Form | Timesheet | Revision | Human Resource ► Form ► Timesheet ► Revision
|  |  | Cancelation | Human Resource | Form | Timesheet | Cancelation | Human Resource ► Form ► Timesheet ► Cancelation
| Report | Data List | Business Trip | Human Resource | Report | Data List | Business Trip | Human Resource ► Report ► Data List ► Business Trip
|  |  | Piecemeal | Human Resource | Report | Data List | Piecemeal | Human Resource ► Report ► Data List ► Piecemeal
|  |  | Timesheet | Human Resource | Report | Data List | Timesheet | Human Resource ► Report ► Data List ► Timesheet
Production | Form | Bill Of Material | Submit | Production | Form | Bill Of Material | Submit | Production ► Form ► Bill Of Material ► Submit
|  |  | Revision | Production | Form | Bill Of Material | Revision | Production ► Form ► Bill Of Material ► Revision
|  | Bill Of Material Detail | Submit | Production | Form | Bill Of Material Detail | Submit | Production ► Form ► Bill Of Material Detail ► Submit
|  |  | Revision | Production | Form | Bill Of Material Detail | Revision | Production ► Form ► Bill Of Material Detail ► Revision
|  | Material Product Assembly | Submit | Production | Form | Material Product Assembly | Submit | Production ► Form ► Material Product Assembly ► Submit
|  |  | Revision | Production | Form | Material Product Assembly | Revision | Production ► Form ► Material Product Assembly ► Revision
|  | Material Product Assembly Version | Submit | Production | Form | Material Product Assembly Version | Submit | Production ► Form ► Material Product Assembly Version ► Submit
|  |  | Revision | Production | Form | Material Product Assembly Version | Revision | Production ► Form ► Material Product Assembly Version ► Revision
|  | Material Product Component | Submit | Production | Form | Material Product Component | Submit | Production ► Form ► Material Product Component ► Submit
|  |  | Revision | Production | Form | Material Product Component | Revision | Production ► Form ► Material Product Component ► Revision
| Report | Data List | Bill Of Material | Production | Report | Data List | Bill Of Material | Production ► Report ► Data List ► Bill Of Material
|  |  | Bill Of Material Detail | Production | Report | Data List | Bill Of Material Detail | Production ► Report ► Data List ► Bill Of Material Detail
|  |  | Material Product Assembly | Production | Report | Data List | Material Product Assembly | Production ► Report ► Data List ► Material Product Assembly
|  |  | Material Product Assembly Version | Production | Report | Data List | Material Product Assembly Version | Production ► Report ► Data List ► Material Product Assembly Version
|  |  | Material Product Component | Production | Report | Data List | Material Product Component | Production ► Report ► Data List ► Material Product Component
Project | Form | Project | Submit | Project | Form | Project | Submit | Project ► Form ► Project ► Submit
|  |  | Revision | Project | Form | Project | Revision | Project ► Form ► Project ► Revision
|  | Project Section | Submit | Project | Form | Project Section | Submit | Project ► Form ► Project Section ► Submit
|  |  | Revision | Project | Form | Project Section | Revision | Project ► Form ► Project Section ► Revision
|  | Project Section Item | Submit | Project | Form | Project Section Item | Submit | Project ► Form ► Project Section Item ► Submit
|  |  | Revision | Project | Form | Project Section Item | Revision | Project ► Form ► Project Section Item ► Revision
|  | Project Section Item Work | Submit | Project | Form | Project Section Item Work | Submit | Project ► Form ► Project Section Item Work ► Submit
|  |  | Revision | Project | Form | Project Section Item Work | Revision | Project ► Form ► Project Section Item Work ► Revision
| Report | Data List | Project | Project | Report | Data List | Project | Project ► Report ► Data List ► Project
|  |  | Project Section | Project | Report | Data List | Project Section | Project ► Report ► Data List ► Project Section
|  |  | Project Section Item | Project | Report | Data List | Project Section Item | Project ► Report ► Data List ► Project Section Item
|  |  | Project Section Item Work | Project | Report | Data List | Project Section Item Work | Project ► Report ► Data List ► Project Section Item Work
Supply Chain | Form | Delivery Order | Submit | Supply Chain | Form | Delivery Order | Submit | Supply Chain ► Form ► Delivery Order ► Submit
|  |  | Revision | Supply Chain | Form | Delivery Order | Revision | Supply Chain ► Form ► Delivery Order ► Revision
|  |  | Cancelation | Supply Chain | Form | Delivery Order | Cancelation | Supply Chain ► Form ► Delivery Order ► Cancelation
|  | Procurement Requisition | Submit | Supply Chain | Form | Procurement Requisition | Submit | Supply Chain ► Form ► Procurement Requisition ► Submit
|  |  | Revision | Supply Chain | Form | Procurement Requisition | Revision | Supply Chain ► Form ► Procurement Requisition ► Revision
|  |  | Cancelation | Supply Chain | Form | Procurement Requisition | Cancelation | Supply Chain ► Form ► Procurement Requisition ► Cancelation
|  |  | Settlement | Supply Chain | Form | Procurement Requisition | Settlement | Supply Chain ► Form ► Procurement Requisition ► Settlement
|  | Purchase Order | Submit | Supply Chain | Form | Purchase Order | Submit | Supply Chain ► Form ► Purchase Order ► Submit
|  |  | Revision | Supply Chain | Form | Purchase Order | Revision | Supply Chain ► Form ► Purchase Order ► Revision
|  |  | Cancelation | Supply Chain | Form | Purchase Order | Cancelation | Supply Chain ► Form ► Purchase Order ► Cancelation
|  |  | Settlement | Supply Chain | Form | Purchase Order | Settlement | Supply Chain ► Form ► Purchase Order ► Settlement
|  | Stock Opname | Submit | Supply Chain | Form | Stock Opname | Submit | Supply Chain ► Form ► Stock Opname ► Submit
|  |  | Revision | Supply Chain | Form | Stock Opname | Revision | Supply Chain ► Form ► Stock Opname ► Revision
|  |  | Cancelation | Supply Chain | Form | Stock Opname | Cancelation | Supply Chain ► Form ► Stock Opname ► Cancelation
|  | Warehouse Inbound | Submit | Supply Chain | Form | Warehouse Inbound | Submit | Supply Chain ► Form ► Warehouse Inbound ► Submit
|  |  | Revision | Supply Chain | Form | Warehouse Inbound | Revision | Supply Chain ► Form ► Warehouse Inbound ► Revision
|  |  | Cancelation | Supply Chain | Form | Warehouse Inbound | Cancelation | Supply Chain ► Form ► Warehouse Inbound ► Cancelation
|  | Warehouse Outbound | Submit | Supply Chain | Form | Warehouse Outbound | Submit | Supply Chain ► Form ► Warehouse Outbound ► Submit
|  |  | Revision | Supply Chain | Form | Warehouse Outbound | Revision | Supply Chain ► Form ► Warehouse Outbound ► Revision
|  |  | Cancelation | Supply Chain | Form | Warehouse Outbound | Cancelation | Supply Chain ► Form ► Warehouse Outbound ► Cancelation
| Report | Data List | Delivery Order | Supply Chain | Report | Data List | Delivery Order | Supply Chain ► Report ► Data List ► Delivery Order
|  |  | Procurement Requisition | Supply Chain | Report | Data List | Procurement Requisition | Supply Chain ► Report ► Data List ► Procurement Requisition
|  |  | Purchase Order | Supply Chain | Report | Data List | Purchase Order | Supply Chain ► Report ► Data List ► Purchase Order
|  |  | Stock Opname | Supply Chain | Report | Data List | Stock Opname | Supply Chain ► Report ► Data List ► Stock Opname
|  |  | Warehouse Inbound | Supply Chain | Report | Data List | Warehouse Inbound | Supply Chain ► Report ► Data List ► Warehouse Inbound
|  |  | Warehouse Outbound | Supply Chain | Report | Data List | Warehouse Outbound | Supply Chain ► Report ► Data List ► Warehouse Outbound
|  | Resume | PR to PO | Supply Chain | Report | Resume | PR to PO | Supply Chain ► Report ► Resume ► PR to PO
|  |  | PO to PI | Supply Chain | Report | Resume | PO to PI | Supply Chain ► Report ► Resume ► PO to PI
|  |  | PI to Payment | Supply Chain | Report | Resume | PI to Payment | Supply Chain ► Report ► Resume ► PI to Payment

## MAIN
ID | LEAD | [7 empty] | U/I FORM | [9 empty] | API | [11 empty] | DATABASE | [11 empty] | REDIS
| REFERENCE ID | LEAD DAYS | PERENCANAAN |  |  | REALISASI |  |  | KOMPONEN | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN |  |  | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN |  |  | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI |  |  | KOMPONEN | PIC | PERENCANAAN |  |  | PERENCANAAN + LEAD TIME |  | REALISASI
|  |  | DURASI | TANGGAL |  | DURASI | TANGGAL |  |  |  | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL | [5 empty] | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL | [5 empty] | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL |  |  |  | DURASI | TANGGAL |  | TANGGAL |  | DURASI | TANGGAL
|  |  |  | AWAL | AKHIR |  | AWAL | AKHIR |  |  |  | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR | [5 empty] | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR | [5 empty] | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR |  |  |  | AWAL | AKHIR | AWAL | AKHIR |  | AWAL | AKHIR
System.Core |  | 0 | 30 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13 | [26 empty] | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13 | [10 empty] | System.Core | 2020-11-13
|  | 0 | [28 empty] | ■ | Stored Procedure
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionBranch_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionBranch_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionBranch_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionCompany_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionCompany_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionCompany_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.Func_TblAppObject_InstitutionRegional_SET | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionRegional_INSERT | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblAppObject_InstitutionRegional_UPDATE | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [28 empty] | ■ | Table
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionBranch | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionCompany | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_InstitutionRegional | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblAppObject_UserRole | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Parameter | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Partition_RemovableRecord_Key | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Partition_RemovableRecord_Parameter | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Schema | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_Table | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblDBObject_User | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_LDAPUserToPerson | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_UserToLDAPUser | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblMapper_UserToUserRole | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblLDAPObject_User | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblRotateLog_API | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
|  | 0 | [29 empty] | - | SchSysConfig.TblRotateLog_FailedUserLogin | Teguh | 30 | 2020-10-14 | 2020-11-13 | 2020-10-14 | 2020-11-13 | 30 | 2020-10-14 | 2020-11-13
System.Authentication.Login | System.Core | 0 | 5 | 2020-11-13 | 2020-11-18 | 3 | 2020-11-13 | 2020-11-16 | [14 empty] | 5 | 2020-11-13 | 2020-11-18 | 2020-11-13 | 2020-11-18 | 3 | 2020-11-13 | 2020-11-16 |  |  |  |  | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [10 empty] | System.Authentication.Login | 2020-11-16
|  | 0 | [7 empty] | Mulyadi | [9 empty] | - | authentication.general.setLogin | Teguh | 3 | 2020-11-13 | 2020-11-16 | 2020-11-13 | 2020-11-16 | 3 | 2020-11-13 | 2020-11-16 | ■ | Stored Procedure
|  | 0 | [17 empty] | - | authentication.general.setLoginBranchAndUserRole | Teguh | 4 | 2020-11-14 | 2020-11-18 | 2020-11-14 | 2020-11-18 | 2 | 2020-11-13 | 2020-11-15 |  | - | dbERPReborn.SchSysConfig.Func_TblLog_UserLoginSession_SET | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblLog_UserLoginSession_INSERT | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.Func_TblLog_UserLoginSession_UPDATE | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [28 empty] | ■ | Table
|  | 0 | [29 empty] | - | dbERPReborn-SysConfig.SchSysConfig.TblLog_UserLoginSession | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
System.Authentication.Logout | System.Core | 0 | 1 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [14 empty] | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 |  |  |  |  | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | [10 empty] | System.Authentication.Logout | 2020-11-14
|  | 0 | [7 empty] | Mulyadi | [9 empty] | - | authentication.general.setLogout | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | ■ | Stored Procedure
|  | 0 | [29 empty] | - | dbERPReborn.SchSysConfig.FuncSys_General_SetUserSessionLogout | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14
|  | 0 | [28 empty] | ■ | Table
Master | System.Core | 0 | 263 | 2020-11-13 | 2021-08-03 | 263 | 2020-11-13 | 2021-08-03 | [14 empty] | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 |  |  |  |  | 244 | 2020-12-02 | 2021-08-03 | 2020-12-02 | 2021-08-03 | 244 | 2020-12-02 | 2021-08-03 | [10 empty] | Master | 2021-08-03
|  | 0 | [7 empty] | Mulyadi | [9 empty] | - | authentication.general.setLogout | Teguh | 1 | 2020-11-13 | 2020-11-14 | 2020-11-13 | 2020-11-14 | 1 | 2020-11-13 | 2020-11-14 | ■ | Stored Procedure
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBloodAglutinogenType_SET | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBloodAglutinogenType_INSERT | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBloodAglutinogenType_UPDATE | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBusinessDocument_SET | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocument_INSERT | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocument_UPDATE | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBusinessDocumentVersion_SET | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentVersion_INSERT | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentVersion_UPDATE | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBusinessDocumentNumbering_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentNumbering_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentNumbering_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBusinessDocumentNumberingFormat_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentNumberingFormat_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentNumberingFormat_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblBusinessDocumentType_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentType_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblBusinessDocumentType_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenFamilyCard_SET | Teguh | 1 | 2021-07-27 | 2021-07-28 | 2021-07-27 | 2021-07-28
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyCard_INSERT
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyCard_UPDATE
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenFamilyCardMember_SET
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyCardMember_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyCardMember_UPDATE
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenFamilyRelationship_SET | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyRelationship_INSERT | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenFamilyRelationship_UPDATE | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenGender_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenGender_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenGender_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenIdentity_SET | Teguh | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | 2021-08-03 | 1 | 2021-08-02 | 2021-08-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenIdentity_INSERT | Teguh | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | 2021-08-03 | 1 | 2021-08-02 | 2021-08-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenIdentity_UPDATE | Teguh | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | 2021-08-03 | 1 | 2021-08-02 | 2021-08-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenIdentityCard_SET | Teguh | 1 | 2021-07-29 | 2021-07-30 | 2021-07-29 | 2021-07-30 | 1 | 2021-07-29 | 2021-07-30
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenIdentityCard_INSERT | Teguh | 1 | 2021-07-29 | 2021-07-30 | 2021-07-29 | 2021-07-30 | 1 | 2021-07-29 | 2021-07-30
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenIdentityCard_UPDATE | Teguh | 1 | 2021-07-29 | 2021-07-30 | 2021-07-29 | 2021-07-30 | 1 | 2021-07-29 | 2021-07-30
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenMaritalStatus_SET | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenMaritalStatus_INSERT | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenMaritalStatus_UPDATE | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCitizenProfession_SET | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenProfession_INSERT | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchMaster.Func_TblCitizenProfession_UPDATE | Teguh | 1 | 2021-07-30 | 2021-07-31 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCountry_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountry_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountry_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCountryAdministrativeAreaLevel1_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel1_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel1_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCountryAdministrativeAreaLevel2_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel2_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel2_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCountryAdministrativeAreaLevel3_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel3_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel3_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCountryAdministrativeAreaLevel4_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel4_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCountryAdministrativeAreaLevel4_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCurrency_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrency_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrency_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCurrencyExchangeRateCentralBank_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrencyExchangeRateCentralBank_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrencyExchangeRateCentralBank_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblCurrencyExchangeRateTax_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrencyExchangeRateTax_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblCurrencyExchangeRateTax_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblDataCompression_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDataCompression_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDataCompression_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblDayOffGovernmentPolicy_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffGovernmentPolicy_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffGovernmentPolicy_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblDayOffNational_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffNational_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffNational_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblDayOffRegional_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffRegional_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblDayOffRegional_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblGoodsModel_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblGoodsModel_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblGoodsModel_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblGoodsType_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblGoodsType_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblGoodsType_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblInstitution_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitution_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitution_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblInstitutionBranch_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitutionBranch_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitutionBranch_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblInstitutionType_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitutionType_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblInstitutionType_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblPeriod_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblPeriod_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblPeriod_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblPerson_SET | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblPerson_INSERT | Teguh
|  | 0 | [29 empty] | - | SchMaster.Func_TblPerson_UPDATE | Teguh
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblPersonAccountEMail_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblPersonAccountEMail_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblPersonAccountEMail_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblPersonAccountSocialMedia_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblPersonAccountSocialMedia_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblPersonAccountSocialMedia_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblProduct_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblProduct_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblProduct_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblProductType_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblProductType_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblProductType_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblQuantityUnit_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblQuantityUnit_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblQuantityUnit_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblReligion_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblReligion_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblReligion_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchData-OLTP-Master.Func_TblTradeMark_SET | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblTradeMark_INSERT | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.Func_TblTradeMark_UPDATE | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [28 empty] | ■ | Table |  | Teguh
|  | 0 | [29 empty] | - | SchMaster.TblBloodAglutinogenType | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.TblBusinessDocument | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.TblBusinessDocumentVersion | Teguh | 1 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-08 | 2021-06-09
|  | 0 | [29 empty] | - | SchMaster.TblBusinessDocumentNumbering | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblBusinessDocumentNumberingFormat | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblBusinessDocumentType | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblCitizenFamilyCard | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenFamilyCardMember | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenFamilyRelationship | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenGender | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenIdentity | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenIdentityCard | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenMaritalStatus | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCitizenProfession | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCountry | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCountryAdministrativeAreaLevel1 | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCountryAdministrativeAreaLevel2 | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCountryAdministrativeAreaLevel3 | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCountryAdministrativeAreaLevel4 | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCurrency | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCurrencyExchangeRateCentralBank | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblCurrencyExchangeRateTax | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblDataCompression | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblDayOffGovernmentPolicy | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblDayOffNational | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblDayOffRegional | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblGoodsModel | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblGoodsType | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblInstitution | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblInstitutionBranch | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblInstitutionType | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblPeriod | Teguh | 1 |  |  |  |  | 1
|  | 0 | [30 empty] | SchMaster.TblPerson | Teguh | 1 |  |  |  |  | 1
|  | 0 | [29 empty] | - | SchMaster.TblPersonAccountEMail | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblPersonAccountSocialMedia | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblProduct | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblProductType | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblQuantityUnit | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblReligion | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
|  | 0 | [29 empty] | - | SchMaster.TblTradeMark | Teguh | 1 | 2020-12-02 | 2020-12-03 | 2020-12-02 | 2020-12-03 | 1 | 2020-12-02 | 2020-12-03
Budgeting.Form.Budget | System.Core | 95 | 95 | 2021-02-16 | 2021-05-22 | 95 | 2021-02-16 | 2021-05-22 | [14 empty] | 1 | 2021-02-16 | 2021-02-17 | 2021-05-22 | 2021-05-23 | 1 | 2021-02-16 | 2021-02-17 |  |  |  |  | 1 | 2021-05-21 | 2021-05-22 | 2021-08-24 | 2021-08-25 | 1 | 2021-05-21 | 2021-05-22 | [10 empty] | Budgeting.Form.Budget | 2021-05-22
|  | 95 | [7 empty] | Mulyadi | [9 empty] | - | transaction.read.dataList.budgeting.getBudget | Teguh | 1 | 2021-02-16 | 2021-02-17 | 2021-05-22 | 2021-05-23 | 1 | 2021-02-16 | 2021-02-17 | ■ | Stored Procedure
|  | 95 | [29 empty] | - | SchData-OLTP-Budgeting.Func_TblBudget_SET | Teguh | 1 | 2021-05-21 | 2021-05-22 | 2021-08-24 | 2021-08-25 | 1 | 2021-05-21 | 2021-05-22
|  | 95 | [29 empty] | - | SchBudgeting.Func_TblBudget_INSERT | Teguh | 1 | 2021-05-21 | 2021-05-22 | 2021-08-24 | 2021-08-25 | 1 | 2021-05-21 | 2021-05-22
|  | 95 | [29 empty] | - | SchBudgeting.Func_TblBudget_UPDATE | Teguh | 1 | 2021-05-21 | 2021-05-22 | 2021-08-24 | 2021-08-25 | 1 | 2021-05-21 | 2021-05-22
|  | 95 | [28 empty] | ■ | Table
|  | 95 | [29 empty] | - | SchBudgeting.TblBudget | Teguh | 1 | 2021-05-21 | 2021-05-22 | 2021-08-24 | 2021-08-25 | 1 | 2021-05-21 | 2021-05-22
2020-11-13
Formulas:
TANGGAL = IF(COUNT([TANGGAL], [TANGGAL], [TANGGAL], [TANGGAL])=0, "", MIN([TANGGAL], [TANGGAL], [TANGGAL], [TANGGAL]))
TANGGAL = IF(COUNT([TANGGAL, row below]:AQ34)=0, "", MIN([TANGGAL, row below]:AQ34))
AKHIR = IF(COUNT([AKHIR], [AKHIR], [AKHIR], [AKHIR])=0, "", MAX([AKHIR], [AKHIR], [AKHIR], [AKHIR]))
AKHIR = IF(COUNT([AKHIR, row below]:AR34)=0, "", MAX([AKHIR, row below]:AR34))
PERENCANAAN + LEAD TIME = IF(COUNT([PERENCANAAN + LEAD TIME, row below]:AS34)=0, "", MIN([PERENCANAAN + LEAD TIME, row below]:AS34))
PERENCANAAN + LEAD TIME = IF(OR(EXACT([PERENCANAAN],""), EXACT([TANGGAL],"")), "", [TANGGAL]+[LEAD DAYS])

## PARAMETER
VLOOKUP HEIGHT | 1000
Current Date Time | 2021-11-09 18:23